## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a developer, I want to submit a bug report with a title, description, reproduction steps, environment, and raw logs so that the defect is captured as a complete, structured record. | Must | - | Ragav K | Done
1 | 1 | US-02 | As a developer, I want to attach log, PDF, DOCX, image, JSON, and zip files so that I do not have to paste a large stack trace into the form. | Must | US-01 | Ragav K | Done
1 | 1 | US-03 | As the system, I want to load historical defect corpora from CSV, JSON, JSONL, XLS, and XLSX exports so that past defects can be searched. | Must | - | Ragav K | Done
1 | 1 | US-04 | As the system, I want a persistent vector index over the historical corpus so that semantically similar defects are retrieved even when they share no vocabulary. | Must | US-03 | Ragav K | Done
1 | 1 | US-05 | As the system, I want a lexical fallback matcher so that retrieval still returns results when no vector index has been built. | Should | US-03 | Ragav K | Done
2 | 2 | US-06 | As a developer, I want the log to be parsed into an exception, root exception, failing frame, and call stack so that I do not read the trace by hand. | Must | US-01 | Ragav K | Done
2 | 2 | US-07 | As a triage lead, I want each report classified by severity, priority, likely component, and bug category so that queue ordering is automatic. | Must | US-01 | Ragav K | Done
2 | 2 | US-08 | As the system, I want an orchestrator that runs the agents in order and isolates a failing agent so that one exception does not lose the whole analysis. | Must | US-06, US-07 | Ragav K | Done
2 | 2 | US-09 | As a developer, I want an evaluation harness that measures parsing and triage accuracy so that a change can be shown not to regress. | Should | US-08 | Ragav K | Done
3 | 3 | US-10 | As a developer, I want a probable root cause with confidence and cited historical defects so that I can verify the claim instead of trusting it. | Must | US-04, US-08 | Ragav K | Done
3 | 3 | US-11 | As a triage lead, I want previously reported defects flagged as duplicates above a confidence threshold so that the same bug is not worked twice. | Must | US-04 | Ragav K | Done
3 | 3 | US-12 | As a developer, I want a recommended fix with verification steps and a stated basis so that I know whether it came from history or from inference. | Must | US-10, US-11 | Ragav K | Done
3 | 3 | US-13 | As a developer, I want the findings shown in one structured dashboard with Markdown and JSON downloads so that the analysis can be shared. | Must | US-12 | Ragav K | Done
4 | 4 | US-14 | As an engineering manager, I want recurring themes, component hotspots, and systemic patterns across all submissions so that I can act on the portfolio, not one defect. | Must | US-13 | Ragav K | Done
4 | 4 | US-15 | As a reviewer, I want a confirmed fix written back into the knowledge base and indexed immediately so that the next occurrence is answered from a proven repair. | Must | US-04, US-12 | Ragav K | Done
4 | 4 | US-16 | As a developer, I want end-to-end validation across several corpus sizes, including an empty corpus, so that degraded behaviour is measured rather than assumed. | Must | US-15 | Ragav K | Done
4 | 4 | US-17 | As a reviewer, I want complete technical documentation, a milestone report, and a scripted demonstration so that the work can be assessed without reading the code. | Could | US-16 | Ragav K | Done
- | - | US-18 | As a reviewer, I want findings written back to an issue tracker so that triage happens where the team already works. | Won't | US-13 | Ragav K | Deferred to a later release
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours | [7 empty] | Row 3 = total remaining effort (hours)
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 264 | 249 | 224.4 | 203.6 | 174 | 143.4 | 121.6 | 89.1 | 68.2 | 35.7 | 6 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG (30-Jun-2026 to 09-Jul-2026)
US-01 | T1.1 | Study defect triage workflows, RAG, semantic similarity, and agent orchestration | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Analysis | Completed | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.2 | Design the system architecture, agent responsibilities, and orchestration flow | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Design | Completed | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.3 | Build the Streamlit bug submission form with field validation | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T1.4 | Implement file upload and text extraction for PDF, DOCX, image, JSON, and zip | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.5 | Implement local JSON persistence for submissions and reports | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T1.6 | Write the historical corpus loader for CSV, JSON, JSONL, XLS, and XLSX | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T1.7 | Build the embedding pipeline and the persistent ChromaDB index | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T1.8 | Implement the lexical fallback matcher and bound its latency | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Development | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T1.9 | Test submission, extraction, and retrieval paths | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Testing | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG (10-Jul-2026 to 21-Jul-2026)
US-06 | T2.1 | Implement per-language stack trace parsers for Python, Java, and JavaScript | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Development | Completed | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T2.2 | Implement the generic fallback parser for logs with no recognised language | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Development | Completed | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T2.3 | Implement root-exception and failure-frame selection per language | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Development | Completed | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T2.4 | Build the triage agent for severity, priority, component, and category | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T2.5 | Define the typed Pydantic contracts for agent results | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Design | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T2.6 | Build the orchestrator with fault isolation and a stable result envelope | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T2.7 | Build the 60-report evaluation harness and record the baseline | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Testing | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-09 | T2.8 | Write unit tests for parsing, triage, and orchestration | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Testing | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG (22-Jul-2026 to 31-Jul-2026)
US-10 | T3.1 | Move retrieval into the orchestrator so all agents share one search | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T3.2 | Build the root cause agent with ranked, cited evidence items | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T3.3 | Build the duplicate detection agent and tune the confidence threshold | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T3.4 | Build the remediation agent with historical, diagnostic, and none bases | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T3.5 | Build the tabbed findings dashboard with severity and confidence display | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T3.6 | Add Markdown and JSON report downloads and the submission history view | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Development | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0
US-10 | T3.7 | Write the Milestone 3 agent and orchestrator test suites | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Testing | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-13 | T3.8 | Update the architecture, agent, and retrieval documentation | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Documentation | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG (01-Aug-2026 to 10-Aug-2026)
US-14 | T4.1 | Implement the pure analytics aggregation over stored submissions | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Development | Completed | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T4.2 | Build the defect pattern analytics agent and the systemic issue rules | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Development | Completed | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T4.3 | Build the analytics dashboard with distributions, hotspots, and trend | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Development | Completed | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T4.4 | Implement knowledge base write-back for a reviewer-confirmed fix | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Development | Completed | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T4.5 | Add live index upsert and synchronous fallback cache rebuild on confirmation | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Development | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T4.6 | Build the 48-run labelled end-to-end validation harness | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Testing | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T4.7 | Fix the defects the validation harness exposed and re-run the suite | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Testing | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.3 | 2.7 | 0 | 0 | 0 | 0 | 0
US-17 | T4.8 | Write the milestone report, changelog, and the five-submission demo script | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Documentation | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-16 | T4.9 | Run the production readiness audit and the full regression suite | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Testing | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | No decision on whether to fine-tune a model or retrieve from history. | Chose retrieval: the corpus grows continuously and fine-tuning would mean retraining per defect.
Sprint 1 | Day 5 | Uploaded PDF and DOCX logs were extracted as empty text. | Added per-format extraction and a fixture for each supported upload type.
Sprint 1 | Day 8 | Building the vector index over the full export was too slow to iterate on. | Committed a 3,600-record sample corpus and kept the full export out of the default build.
Sprint 1 | Day 9 | A fresh clone retrieved nothing because the committed datasets held only issue ids. | Committed gitbugs/samples/ and pointed both retrieval paths at it.
Sprint 2 | Day 3 | Unanchored exception patterns quoted ordinary prose back as an exception type. | Anchored the language patterns to line start and kept the generic scanner as a fallback.
Sprint 2 | Day 6 | Java exception_type and root_exception were always identical, hiding the Caused by chain. | Reported the thrown exception and the underlying cause separately.
Sprint 2 | Day 8 | A single stack trace was parsed up to five times and reported phantom frames. | Stopped concatenating the overlapping submission fields before parsing.
Sprint 2 | Day 10 | One agent raising an exception lost the entire analysis. | Recorded agent errors under metadata.agent_errors and let later stages continue.
Sprint 3 | Day 2 | Each agent searched independently and could cite contradictory histories. | Moved retrieval into the orchestrator and passed one shared context forward.
Sprint 3 | Day 4 | Duplicate detection was silent on the fallback backend, whose scores never reached the threshold. | Made the confidence floor backend-aware.
Sprint 3 | Day 6 | Remediation reached the no-recommendation branch on every submission. | Added a diagnostic basis capped below any historically grounded confidence.
Sprint 3 | Day 8 | Overall confidence mixed duplicate similarity with agent confidence, conflating two units. | Separated the scales and documented how the overall figure is composed.
Sprint 4 | Day 3 | Submissions with no agent output would have formed a growing fake Unknown hotspot. | Excluded them from the theme and component groupings instead of bucketing them.
Sprint 4 | Day 5 | A confirmed fix was not retrievable until the whole index was rebuilt. | Upserted the record into the live index and rebuilt the fallback cache at write time.
Sprint 4 | Day 7 | Duplicate recall sat at 57% for submissions assembled without submitted_text. | Included the stack trace in the retrieval query; recall rose to 86% and F1 to 0.92.
Sprint 4 | Day 9 | The layout ran off the right of the screen at narrow widths. | Constrained the container width and re-ran the interface checks.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 30-Jun-2026 | 09-Jul-2026 | Ragav K | Writing the architecture and agent contracts down before coding. | Treating dataset files as usable without opening them first. | Keeping the whole pipeline runnable offline with no API key. | Committed a small sample corpus so a fresh clone works end to end.
2 | Sprint 2 | 10-Jul-2026 | 21-Jul-2026 | Ragav K | Adding a regression test for every parsing asymmetry found by hand. | Concatenating overlapping fields before parsing, which produced phantom frames. | Fault isolation between agents, which kept partial results useful. | Built the 60-report evaluation harness and recorded a baseline to compare against.
3 | Sprint 3 | 22-Jul-2026 | 31-Jul-2026 | Ragav K | Making every agent cite the bug ID and similarity behind each claim. | Letting agents search independently and cite different histories. | Preferring a low-confidence honest answer over a confident invented one. | Moved retrieval into the orchestrator and shared one context across all agents.
4 | Sprint 4 | 01-Aug-2026 | 10-Aug-2026 | Ragav K | Hand-labelling expected results instead of deriving them from the agents' own rules. | Assuming graceful degradation without testing the zero-record corpus. | Documenting each defect and its fix in the changelog as it was closed. | Ran 48 labelled pipeline runs and fixed the six defects they exposed.