## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ragav K | 09-Jul-2026 | The committed knowledge base held only issue and duplicate ids, and the local matcher globbed the gitignored full exports, so a fresh clone retrieved nothing. | Sprint 1 | Ragav K | Logical | Committed gitbugs/samples/ (9 projects, 3,600 defects) and pointed both retrieval paths at it. | 09-Jul-2026 | Closed | Found while testing a clean checkout.
2 | Ragav K | 09-Jul-2026 | The vector index had no build entry point, so semantic retrieval never ran. | Sprint 1 | Ragav K | Logical | Added scripts/build_index.py and surfaced index status in the application. | 09-Jul-2026 | Closed | Fallback retrieval masked the problem.
3 | Ragav K | 21-Jul-2026 | An uploaded JSON log kept its stack trace as an escaped string, so the line-anchored parsers found no frames at all. | Sprint 2 | Ragav K | Logical | Decoded JSON uploads to plain text before parsing. | 18-Jul-2026 | Closed | Covered by a sample_uploads fixture.
4 | Ragav K | 21-Jul-2026 | Java exception_type and root_exception were always identical, which hid the Caused by chain. | Sprint 2 | Ragav K | Logical | Reported the thrown exception and the underlying cause separately. | 19-Jul-2026 | Closed | Python chaining semantics deliberately left unchanged.
5 | Ragav K | 21-Jul-2026 | Log analysis concatenated five overlapping submission fields, so one stack trace was parsed up to five times and reported as repeated phantom frames. | Sprint 2 | Ragav K | Logical | Parsed the assembled text once instead of each overlapping field. | 20-Jul-2026 | Closed | Caused visibly wrong frame counts in the report.
6 | Ragav K | 21-Jul-2026 | The fallback parser could quote a structural line such as a closing brace as the failure point. | Sprint 2 | Ragav K | Logical | Excluded structural lines from failure-frame selection. | 21-Jul-2026 | Closed
7 | Ragav K | 21-Jul-2026 | agents/__init__.py and models/__init__.py contained duplicated module bodies whose second __all__ dropped earlier exports. | Sprint 2 | Ragav K | Maintainability | Removed the duplicated bodies and restored the full export list. | 21-Jul-2026 | Closed | Imports silently resolved to the wrong symbols.
8 | Ragav K | 21-Jul-2026 | Bug submission caught every exception and reported one generic message, so the real cause was lost. | Sprint 2 | Ragav K | Standards | Logged the underlying cause and surfaced a specific message. | 21-Jul-2026 | Closed
9 | Ragav K | 31-Jul-2026 | Duplicate detection was effectively silent on the fallback backend, whose similarity scores never reached the semantic threshold. | Sprint 3 | Ragav K | Logical | Made the confidence floor backend-aware. | 26-Jul-2026 | Closed
10 | Ragav K | 31-Jul-2026 | Issue-tracker Resolution statuses such as Fixed were treated as fix text and could be recommended as a remediation. | Sprint 3 | Ragav K | Logical | Kept the workflow outcome separately as resolution_status and excluded it from fix text. | 27-Jul-2026 | Closed | The most user-visible correctness defect in the sprint.
11 | Ragav K | 31-Jul-2026 | Remediation could never recommend a fix, because issue-tracker exports record a workflow status rather than repair text, so every submission reached the no-recommendation branch. | Sprint 3 | Ragav K | Logical | Added a diagnostic basis derived from the exception and root cause, capped below any historically grounded confidence. | 29-Jul-2026 | Closed
12 | Ragav K | 31-Jul-2026 | A crashed agent was rendered as a clean negative finding rather than as a failure. | Sprint 3 | Ragav K | User Interface | Rendered agent errors distinctly from a genuine no-result outcome. | 30-Jul-2026 | Closed
13 | Ragav K | 31-Jul-2026 | Overall confidence averaged duplicate similarity together with agent confidence percentages, conflating two different units. | Sprint 3 | Ragav K | Logical | Separated the two scales and documented how the overall figure is composed. | 30-Jul-2026 | Closed
14 | Ragav K | 31-Jul-2026 | The sidebar was hidden by display:none while render_sidebar() kept writing submission history into it, making that feature unreachable. | Sprint 3 | Ragav K | User Interface | Restored the sidebar and its submission history. | 31-Jul-2026 | Closed
15 | Ragav K | 10-Aug-2026 | An exception prefixed by a log level or field name, such as FATAL: SecurityError, was missed entirely because the language patterns are line-anchored. | Sprint 4 | Ragav K | Logical | Gave the generic scanner a turn when, and only when, the language parser found no exception. | 05-Aug-2026 | Closed | Found by the end-to-end validation harness.
16 | Ragav K | 10-Aug-2026 | Plural component keywords were unclassified, so notifications fell through to Other. | Sprint 4 | Ragav K | Logical | Added plural forms to the component keyword rules. | 05-Aug-2026 | Closed
17 | Ragav K | 10-Aug-2026 | A payment outage phrased as a verb triaged as Medium, because only the noun form appeared in the severity rules. | Sprint 4 | Ragav K | Logical | Added the verb forms to the severity rules. | 05-Aug-2026 | Closed
18 | Ragav K | 10-Aug-2026 | Retrieval ignored the stack trace for submissions assembled without submitted_text, so the same defect matched as text but was missed as a record. | Sprint 4 | Ragav K | Logical | Included the stack trace in the retrieval query. Duplicate recall rose from 57% to 86% and F1 from 0.73 to 0.92. | 06-Aug-2026 | Closed | Largest measured accuracy gain of the project.
19 | Ragav K | 10-Aug-2026 | The fallback retrieval path discarded the resolution and root_cause columns, so a confirmed fix could not ground a recommendation until the index was rebuilt. | Sprint 4 | Ragav K | Logical | Carried both columns through the fallback path, which would otherwise have left knowledge base growth inert by default. | 06-Aug-2026 | Closed
20 | Ragav K | 10-Aug-2026 | Writing a confirmed fix left the fallback corpus cache cold, so the next search could silently return nothing inside the interactive budget. | Sprint 4 | Ragav K | Logical | Rebuilt the corpus cache synchronously at confirmation time. | 07-Aug-2026 | Closed
21 | Ragav K | 10-Aug-2026 | PyPDF2 had reached end of life and the dependency set was unpinned. | Sprint 4 | Ragav K | Maintainability | Moved to pypdf, pinned the dependencies, and adopted Ruff. | 07-Aug-2026 | Closed
22 | Ragav K | 10-Aug-2026 | The layout ran off the right of the screen at narrow window widths. | Sprint 4 | Ragav K | User Interface | Constrained the container width and re-ran the interface checks. | 09-Aug-2026 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others